## Sheet1
Goal: Create an Automated reporting and Vendor Management System, merge with Personnel.com, create and grow market, identify service and automation niches, etc…
Term | Description | Goal or Objective | Problem | Dependancies | Goal Date | Folder
Short | Backup and Disaster Recovery Plan, finish documenting and implementing | Communicate Design concept and theory, protect from future data loss while also allowing data to be recovered in less than a day locally from within each branch | Current backup plan was unmanaged and maintained, and didn't not perform as expected [however major data loss was averted] | Backup hardware
Short | Judy's Cyma / Temps duplicate and trplicate posting listing issue | Correct Temps posting to Cyma issue | Every week it gives payroll back to sometime in August and it has to either be posted and deleted or have Richard go in a delete it from the posting batch.
Short | Research and Select Server Anti-Virus product, deploy it to servers | Protect servers from virus and other malicious software | Current AVG license expired; needs renewed or another product found. | Anti-Virus software
Short | Group Timecard | Automate Time capture, management, approval, pay and reporting | Data entry and communcation issues, burdening manual processes associated with completed sub-procedure related to overal payrolling sub-procedure of Staffing / Personnel services | Electronic Tmecard element defined. Pending debugging during phased roll-out and deployment
Short | Combined invoices are printing as if they are 'A'. | Combined Invoices print together on one page | They're not
Short | CreateApplication: Bug: Stuff not changing in Temps | Have information in Temps change or update when people are enrolled. | When people update or get enrolled some [or all?] of the information in Temps is not changing
Short | Timeclock Applicance | Create badge scanner timeclock system that integrates with our own VMS [Jackie/IES]
Short | Timeclock Applicance | Create an appliance that can be installed at client sites, and remotely managed and monitored, that automates the collection of employee clock-in data and association with relevent Cost-Center and Department, and that then automatically feeds into Group Timecard app for dove-tailing into timecard and payrolling procesdures
Short | Maidsource.net search results | When doing a search for housekeeping, housecleaning, janitorial etc. for twin, Boise etc. we want [Need] to be at the top of the search results. Our maidsource site (or another) needs SEO and fixed with Google, yahoo, etc. with the necessary keywords etc., blog integration, social media content, job listings [dynamica content] from personnelinc.com [and personnel.com eventually], etc. | WE DON’T EVEN REGISTER [in the search results].Attributed to sites lack of traction in market areas like Boise.
Short | Online Employee Timecard Error | Fix issue so that new employees can access online timecard | Microsoft OLE DB Provider for ODBC Drivers error '80040e14', [MySQL][ODBC 5.1 Driver][mysqld-5.5.28]You have an error in your SQL syntax; check the manual that corresponds to your MySQL server version for the right syntax to use near '' at line 1, /include/system/tools/timecardEmp.asp, line 218 | Group Timecard
Short | W2's: 2012 Assets need added to system | W2's downloaded online for applicants | Need to setup this years form and push over a copy of finalized yearly data to system to push and merge onto form for downloads | 2012 form, script extension, final database with yearly W2 data from Temps
Short | Interview Script: Bug: Notes not transfering | Identify and correct situations where Applicant notes dissappear and or don't transfer, with no error | Some Applicants Interview notes do not transfer
Short | Interview Script | Exctend form to include additionally requested information, address issues preventing some information from transferring and extend reach of Applicant Search tool to include Interview data | Priority is some information doesn't transfer Desired is the extended search attributes | None, Core
Short | Optimize Guest Resume Submittal | Increase resume pool: - Increase quality of applicant pool; and - Necessary to establish an existing resume pool in order to later feed, and use, to build Personnel.com [necessary for national / global presence] | We are getting a few but would like to see more. I guess when I log onto the page it is not apparent that one can continue as guest and must register first.
Short | Usage Report | Correct Inaccurate Reporting Information | Random errors and annomolies in how the VMS is interpeting information entered differently for customers data across the companies and years | Correct Info is Needed to Feed Bill-Pay and for customer perceptoin
Short | Review the consistency in our Personnel Plus policy statements, and all offices display and use the same such documents [tony] |  |  | Kelli and Christina reviewing documents
Short | Personnel.com: Users | Complete adapting Personnel.com backend over to use the VMS [started, about 40% complete] | Was not a way to register users on both sites so that a member on Peronnelinc.com is also a member of Personnel.com. By doing this we can use the Job Postings, Applications and Resume resources from Personnelinc.com to build and drive momentum behind Personnel.com [also fixes users not being able to login or register currently on personnel.com]
Long | Squid, Reverse proxy HTTPS | Increased performance for web traffic as usage builds | Binding SSL certificate to Squid
Long | Migrate personnelplus.net to personnelinc.com | Better name recognition, SEO, and unified marketing. | When users use are services and transverse between HTTPS, HTTP and personnelinc.com and personnelplus.net our site is split up several different ways reducing our ratings in search engines and increasing our overall complexity of things
Long | Unify all web services through single SSL portal: https://www.personnelinc.com | Set everything to run though HTTPS | Originally when our site was setup best practive dictated that there should be a public unsecure site and private secure side in order to partition information and services and facilitate search engine traffic. Now it's more efficient and best practive just to run everything through HTTPS | Security certificate for *.personnelinc.com
Short | SFTP | Secure "Back-Door" like access to Zions bank | In order to automate financial transactions NACHA formatted files need to be uploaded to financial institutions via Secure File Transfer Protocol | Depends on SSL certificate
Short | Online Payment and Bill Pay | Complete NACHA service to format Routing, Account and Payment amount into Industry standard NACHA file | Address Billing and Invoicing issues | Usage Report, SFTP service
Long | Automate our Client Relationship Management | Optmize our marketing efforts and ensure consistency and thoroughness in how our forward facing processes communicate knowledge and other relavent information like Marketing | Customers getting multiple calls and or contacts on the same day by multiple internal associates and or clients not being followed up with consistently resulting in lost revenue | Completed Marketing Plan needed before automation can be completed
Long | Personnel.com | Position Personnel.com as a site for the “national “ and international audience, needs to remain flexible in that regard. | There needs to be thought on how to retain the National and Local attributes of Personnel.com while also using Personnelinc.com to 'jump-start' it
Long | Employer Login | Review and integrate elements from here: http://search4.smartsearchonline.com/provisional/jobs/client_membership.asp | Site flow is ambiguous and confusing, and in areas unclear
Short | VMS Change & Notes tracking | Track Applicant, Client and Staff information changes and updates | Inconsistencies appear in certain Knowledge pieces under certain change and update scenarios | Notes Class, Enrollment Method
Short | Notes Class | Cannot consistentently syncronize information across all mediums due to the absence of a consisten and agreed upon Note Class across branches
Short | Appointments | Automatically display a notification on users Startpage [or desktop] to remind of weekly / daily appointments
Long | Uniform Sales Scripts | Consisten unified sales effort across all marketing mediums to align corporate perception | Identify areas to include in sales effort and dialogue about goals and objectives | Identify marketing Mediums, Key TOOLS that clients want, and align our focus with those.
Short | Marketing Brochure | Develop a brochure for marketing our VMS abilities and staffing program | Currently do not have a VMS specifically tailored marketing brochure to showcase, highlight and demonstrate what sets our system apart from the rest and offers what clients can't get anywhere else | Consisten marketing Copy [content / material] |  | Projects / VMS Marketing Brochure
Short | Prospective Clients Features Presentation | Create a presentation to show prospective clients how our VMS can streamline contingent hiring, enable clients to compare candidates, approve timecards, manage spending and also is Very user friendly | Example: http://www.beeline.com/software/contingent-staffing/ | The stuff we claim we have, working.
| Online Presentation Describing our VMS | Package a marketable user experience that can be offered to clients and explain how they need something, that they currently don't have, and that they can't live without. | Communication, prioritization… Page syncronization.
| Interview Object | Complete defining "Inerview" knowledge piece so it can be categorized and folded with other projects and knowledge pieces
| Client Prospecting | Ability to report and identify former clients that Applicants have worked for | Branches are unable to “query” the information from the interview script that tells us who has “worked for a staffing service before".
Short | Net Applicant Skills | Syncronize, and make available, skills online that applicants are selecting with the skills internally that we think Applicants are requesting | An artifact from the days of branches operating as indepentant islands, and each with their own subset of 800 - 1000 skills, some skills are not being transferred from online profile
Long | 2010 W2's | Letters continueing to request corrected wage information | Have repetively called and contacted the IRS to verify that they have received the corrections and updated wage information, however continue to receive acertions that such has not happened yet? | 2010 Wage Accouting
Short | Group Timecard - Auto save | Allow ATDLawn to log in and manage time online | Auto-Save portion of tool keeps crashing when users attempts to enter information | Group Timecard Model
Short | Interview Script: Bug | Identify and fix problem areas in user data entry form and or script to allow for, or sanitize, longer data | Some attributes [like 'kind_of_work'] crash script siting "Data too long"
Short | Incomplete Applications | Prompt and attempt to dissuade users from leaving page, if they do attempt to send them a follow up email in a few days inviting them back to finish and or notifying them of new job postings | Some users start process and don't complete. Would like to automate the process of getting them to come back | None
Short | Enter and Create Activities online | Be able to click and edit, and or create, an activity via the web browser just like you would enter information for facebook or other ajax power sites. This allowing portable devices to be utilized for activity entry | Current Activities can only be Viewed online, to be entered on the road requires a cumbersome process of logging into Temps remotely and using the sluggish unintuitive interface | ajax service to feed Applicant and Customer data [similar to Google search suggestions]
Long | Management Web Form | Need front end management form / took to allow client / staff to manage certain attributes of VMS | Unskilled and lack of techincal knowledge amogst certain users has necessitated the creation of additional Tools and forms to allow information to be managed
Long | Quality Assurance Calls | Integrate and Document current procedures [finalized and submitted by Piper] into SOP's | Aligning internal branch procedures and positioning for automation | SOP's master and Formalzing revision procedure
Short | Marketing Plan | Show marketing personnel how to use features of system to collobarate and align objectives of team members | Knowledge of IT and related computing concepts. | Exchange, Calendar Templates
Short | Optimize Personnelinc.com's marketing curb appeal | We need more of a “marketing” orientated webpage to garner interest from potential clients and also to” reduce the clutter” for existing clients. | Site is currently too cluttered and existing clients need to fight to get to where they know they need to go
Long | Blogs | Supplement blog info and content; Google SEO, site-cross promotion, integrate with Social Media | Web crawlers, and users, rely on dynamic and fresh content to ensure a sites credibilty and viabilty | Dynamic blog content and contributations
Long | Skills | Automate Applicant Skills testings | Automate information adition from Applicants and automatically integrate into available online VMS profile available to clients | Applicant Profile, class definitions
Long | Orientation video: Tracking | When an applicant views a video add that activity, and the video they watched, to the Applicants profile [allowing VMS to monitor and track applicant processes, guaranteeing client expectations are consistently met] | Currently we have made the videos available online and distributed through state, but have no way of tracking what an Applicant has watched and or seen, and no way of presenting this info to the client or us | Applicant Profile, class definitions
Long | Drug Testing: Automate procedure [like Inverview script] | Collect drug testing data in a manner similar to Interview and Application data, also collect Photo of test and include with the same [like a Resume submital] and automatically ad to applicants Application attachment | Laborous manual process, automate information collection and filing to free up resources while also guaranteeing consistent repetition of precedure, consistently for every applicant, and gives VMS something to 'ear-mark' in order to track and contribute to Applicants profile | Drug testing form, class definitions
Long | SOP's: Integrate Q/A calls procedure | Document Q/A procedures for future branches and to facilitate consistency | Inconsistance branch procedures; unable to automate | Standard SOP's
Long | Designate Branch Spokesperson for Blogs | Someone to consistantly maintain out presence in social media
Long | SOP's - Folder meeting descisions into SOP's folder
Long | Onling Policy Statements | Inconsistencies exist between policy forms amongst branches and online
Long | Slave Database Server | Need slave MySql databse server built and setup to run in tanden with existing server | Single point of failure; no redundancy. X server goes does, VMS goes down. | Server hardware, server configed
Long | Cluster Web Services across multiple boxes and sites | Introduce web service redundancy | Single point of failure; no redundancy in web services | Server hardware, server configed
Long | Complete Temps MSSQL Database migration | Increased performance and realiability; scalable for VMS. | Current system built around and using file based JET database. They're slow and not scalable, as usership starts being realized VMS is setup to choke. | Temps licensing or working license side-step procedure
Long | Migrate VMS Temps Conduit to use MSSQL | Scalability, performance and thousands of users at once instead of a couple.
Long | Policy Statement Verbiage | Verbiage of policie statements needs to be reviewed and revised [delegated to Kelli I think]
Long | Online Ratings System | Ability for Employers and Us to log in and see in a central area an employees "Rating" | Currently we do not have a progressive tracking system in place for measuring and qualifying an employees performance and quality of work over time | Rating System Workflow, Web forms, email templates, tracking, aggregation and perspective management algorythms, additional brain storming and planning
Short | Secure Online ordering | Tool to let clients order and manage job orders online | Tools was started and mostly completed before being back burned for fear of severing the "personnal" connection we have with out clients when they call us | Order class definitions
Long | Revise VMS Tracking | Reliably track, monitor and report user activity online | Current tracking model was built pre-AJAX and does not capture service events. Almost ALL current VMS interaction is currently service based | Tracking class definitions
Long | Document Applicant and other procedures [like applicant application process, paper-app, interview and placement procedures] | Create workflows for all forward facing and back-office procedures. | Current lack of standardization makes defining expectations defficult and ensuring correct operations and usage of systems across branches. Also have nothing to use for training, and future managemnt of procedure changes | Documented procedures [have partial ones located in SOP's folder]
Long | SOP's / Documentation | A central unified document for storing reference information, decisions, instructions, etc. | Have meeting minutes, descisions, email conversations, etc. that all result in advancing topics and concepts forward, however there is no central place to organize this information so at best its scattered in net_docs and or forgotten in email | Completed SOP's Framework so information can start being contributed by everyone, Office applcation software training for users so they know how too [Richard?]
Long | Mobile App | A mobile app that offers our VMS tools directly from a users mobile device and without a brower | Don't have an app yet.